## Requests
Ref | Received | Requester | Team | Request | Classification of output | Assigned | Due | Status | Delivered | Notes
PI-1052-031 | 1052-08-20 | Dean H and E | Faculty | NSS 1052 Faculty deep dive | Internal | Erra | 1052-10-17 | Done | 1052-10-17 | Report in Reports library
PI-1052-034 | 1052-09-03 | Head of Education | Dept of Education | NSS free text comments for Education | Internal | Erra | 1052-09-10 | Done (declined) | 1052-09-05 | Education has no NSS finalists. Pointed to enrolment survey instead. Requester not pleased.
PI-1052-036 | 1052-09-15 | Head of Admissions | Admissions | Weekly conversion dashboard export | Internal | Teylin | Weekly | Ongoing |  | Automated from 1052-10
PI-1052-039 | 1052-10-01 | Head of P and I | Planning | Faculty awarding gap extract by programme for Council report | Internal | Erra | 1052-10-31 | Open |  | Started 1052-10-03. Paused for NSS deep dive. Not yet QA'd.
PI-1052-041 | 1052-10-20 | Quality | Quality | Exam board marks tables Health programmes | Confidential | Erra | 1053-05-30 | Scheduled |  | Student IDs only
PI-1052-045 | 1052-11-03 | Council (via Secretary) | Governance | Annual report on student outcomes appendix | Internal | Erra | 1052-11-10 | Done | 1052-11-10 | Awarding gap annual report 1051-52
PI-1053-002 | 1053-01-12 | Programme Leader N and C | PST | Student list with pathway and Year 1 placement for allocation | Confidential | Teylin | 1053-01-16 | Done | 1053-01-15 | To Hesta. Names and IDs only.
PI-1053-006 | 1053-02-24 | Dean H and E | Faculty | Gap numbers for Council. By programme. "Thoughts?" | Internal | Quorin | 1053-03-03 | Replied | 1053-03-03 | Asked for definition of gap and audience before producing. See email.
PI-1053-009 | 1053-03-07 | Head of Admissions | Admissions | Conversion by clan for 1053 entry | Internal | Quorin | 1053-03-14 | Replied | 1053-03-12 | Small numbers. Provided species-level only with caveats.
PI-1053-011 | 1053-03-19 | Head of Admissions | Admissions | Interview turnaround times by programme | Internal | Teylin | 1053-03-26 | Done | 1053-03-25
PI-1053-014 | 1053-04-02 | Deans Office (E Fogwhisper) | Faculty | Can Quorin sign off the Dean's Council paper by Friday | Internal | Quorin | 1053-04-09 | Replied (declined) | 1053-04-09 | Figures are last year's and Elf and Dwarf rates swapped in one place. See email.
PI-1053-015 | 1053-04-10 | Programme Support Team (L Lanternwake) | PST | Is there a provider table anywhere in P and I | Internal | Teylin | 1053-04-12 | Done | 1053-04-10 | No. Nice question though.