# INC-0031: Closure note

Information Governance Manager, 7 March 1053. Confidential.

## Summary

On 19 February 1053 a Wellbeing Adviser attached a student's full support plan, instead of the one-page adjustments summary, to an email to the NC-Y2-Teaching distribution list (14 staff). The adviser self-reported within the hour. The incident was contained the same day, the student was informed the following day, and the regulator did not require notification.

## Actions and status

| # | Action | Owner | Status | Verified by |
| --- | --- | --- | --- | --- |
| 1 | Deletion requested from all 14 recipients; confirmations received | IGM | Complete, 14 of 14 by 24 Feb | IGM (confirmations on file) |
| 2 | Copy saved to the Year 2 teaching folder on the Hub to be removed | Programme Leader, Nursing and Care | Complete | Programme Leader confirmed by email 27 Feb: "done" |
| 3 | Review meeting held | IGM | Complete, 26 Feb | Note on file (Head of Student Wellbeing) |
| 4 | Sharing procedure revised: summary generated as a separate file, separate folder, distinct name pattern; bulk requests from faculties not accepted | Head of Student Wellbeing | Draft complete 5 Mar; approval at next IGG | IGM |
| 5 | All advisers briefed | Head of Student Wellbeing | Complete, 3 Mar | Head of Student Wellbeing |

## Lessons

Similar names in the same folder will be confused under time pressure. The fix is structural, not a reminder to be careful.

Faculties requesting Confidential material in bulk against a deadline creates the conditions for error. The revised procedure declines such requests.

Recipients saving an attachment "for the file" is the normal thing to do and is the reason containment must include checking where copies have gone.

## Closure

All actions complete or on track with an owner and date. Incident closed 7 March 1053.

E. Dewscroll

Added to the Data Breach Procedure at version 1.2: removal of copies must be verified by Information Governance, not taken on the owner's confirmation. This incident's action 2 was closed on the Programme Leader's confirmation; under the revised procedure it would be checked directly.