## Run sheet
Time | Activity | Location | Lead | Notes | Status
08:00 | Set-up: stands and signage | Cloister Lawn and Great Hall | Javin (Comms) | Banner from Comms (requested 1 Apr - old name on request!! check) | Pending
09:00 | Staff briefing | Oration Chamber | Mira | All stand staff. Brand guide reminder (Sorell asked) | Booked
09:30 | Doors open | Great Hall | Admissions team | Registration desk x2 | Booked
10:00 | Welcome talk | Oration Chamber | Vice-Chancellor | 10 mins. Slides from Comms | Requested
10:15 | Faculty talks (parallel) | Various | Deans | H and E in the Oration Chamber | Booked
10:00-15:00 | Education stand | Cloister Lawn by the tree | Jaskel | Jaskel's deck is 42 slides. Ask him to use the Comms template? | Discuss
11:00 | Taster workshops | Teaching rooms | Programme leaders | Education C1.04; Nursing skills lab; OT therapy suite | Booked
12:00 | Meet the students | Cloister Lawn | Student ambassadors | 12 ambassadors confirmed | Booked
12:00-14:00 | Lunch (staff rota) | Dining Hall | Hesta (PST) coordinating rota |  | Booked
13:00 | Admissions and funding talk | Oration Chamber | Mira | Contextual offers; first-gen bursary. NOTHING on competitor bursaries | Booked
14:00 | Campus tours | From Great Hall | Ambassadors | 4 tours of 20 | Booked
15:00 | Accommodation talk | Oration Chamber | Accommodation office |  | Requested
16:00 | Close |  | Mira | Feedback forms at exits (paper and QR) | Booked

## Rooms
Room | Booked | Capacity | Notes
Oration Chamber | Y | 200
Great Hall | Y | 400 | Registration and stands
C1.04 | Y | 30 | Education taster (bring a pencil - Jaskel)
Nursing skills lab | Y | 24
OT therapy suite | Y | 16 | Shared with Physio - checked
Cloister Lawn | Y (weather) | n/a | Wet weather: Great Hall overflow

## To do
Item | Owner | Due | Done
Banner artwork to Comms | Mira | 1 Apr | Y (request sent; Sorell queried the name)
Ambassador briefing | Mira | 7 Jun
Feedback form | Teylin (P and I) | 1 Jun
Stand materials: Education | Jaskel | 7 Jun | Jaskel says done. Comms say not approved.
Stand materials: Health | Dagna | 7 Jun
Catering order | Hesta | 1 Jun
Signage (on brand this time please) | Javin | 7 Jun