## Slide 1
Placements: the process
One slide per step. Attempt two. Sept 1052.

## Slide 2
Step 1: Ask providers
  • June: letter to all providers
  • Ask: how many, what pathway, what conditions, anything changed
  • Record replies in Providers tab (col E and F)
  • Chase non-repliers in September
  • Arrow to step 2

## Slide 3
Step 2: Build the list
  • Student list from the record system (Hesta exports it)
  • Add pathway, Year 1 placement, home area
  • Add Wellbeing flags (adjustments Y/N, nothing else)
  • Add student constraints from the form they fill in (hardly anyone fills it in)
  • Arrow to step 3

## Slide 4
Step 3: Allocate
  • Match students to places (the jigsaw)
  • Check capacity tab (formulas broken, check by eye)
  • Check nobody's gone back to a Year 1 placement
  • Check adjustments against provider conditions (no nights etc)
  • Arrow to step 4

## Slide 5
Step 4: Confirm
  • Email each provider: names and start dates only
  • Email each student: provider, mentor if known, start date, link to profile
  • Two weeks before. Aim.
  • Arrow to step 5

## Slide 6
Step 5: Pre-start checks
  • OH cleared? (portal, or letter for Hollowpick)
  • Mandatory training done?
  • Provider extras done? (interview, briefing, boots, form, induction)
  • If no: chase student, delay start, tell provider
  • Arrow to step 6

## Slide 7
Step 6: During
  • Weekly: any issues? (mentor, hours, conduct, wellbeing)
  • Log in Issues tab
  • Escalate: Dagna (conduct), Wellbeing (student), Nyssa (FtP)
  • Arrow to step 7

## Slide 8
Step 7: After
  • Hours confirmed by provider
  • Practice Assessment Record signed
  • Make-up hours arranged if needed
  • Thank-you email to provider (I always do this and it matters more than people think)
  • Back to step 1

## Slide 9
Step 0: When it all goes wrong
  • Provider pulls out: ring Agda, then the list of providers with spare places (Capacity tab), then students in order of travel distance
  • Student without clearance: send home, chase OH, restart next week, tell provider
  • Swap: pull both, tell Dagna
  • This slide is the one that should be a whole document